## Sheet1
Step | Sub-steps | Responsible party | Rate | Duration as-is | Cost as-is | Duration to-be | Cost to-be
Initial Planning (2-4 weeks prior):
| Define the purpose and objectives of the visit. |  |  | (2 days)
| Identify key stakeholders and their roles. |  |  | (1 day)
| Review previous monitoring reports and findings. |  |  | (2 days)
| Develop a monitoring plan, including checklists and protocols. |  |  | (1 week)
| * Schedule the visit with the site and relevant personnel. |  |  | (1 week) |  | 0
Preparation (1-2 weeks prior):
| * Gather necessary monitoring tools and equipment (e.g., forms, devices). |  |  | (2 days) |  | 0
| Prepare a detailed itinerary for the visit. |  |  | (1 day)
| * Communicate the visit schedule and expectations to the site. |  |  | (2 days) |  | 0
| * Ensure all necessary permits or access arrangements are in place. |  |  | (1 week) |  | 0
* Travel to Site (1-2 days before):
Travel to the site location (varies by distance).
Book hotel, airline, rental
Per diem (for meals, etc.)
“Last mile” travel to site (e.g., from hotel/lodging)
On-Site Monitoring (During Visit):
| Introduction and orientation with site staff. |  |  | (1 day)
| * Walkthrough and initial observations. |  |  | (2-3 days) |  | 0
| * Data collection, interviews, and document reviews. |  |  | (3-5 days) |  | 0
| * Adherence to safety protocols and quality assurance. |  |  | (ongoing) |  | 0
| * Daily debrief with site staff and stakeholders. |  |  | (1-2 hours/day) |  | 0
Data Analysis (After Visit):
| * Review and organize collected data. |  |  | (1-2 days) |  | 0
| * Analyze findings against established criteria. |  |  | (2-3 days) |  | 0
| Identify issues, trends, and potential risks. |  |  | (2-3 days)
Report Generation (1-2 weeks after visit):
| * Compile and structure the monitoring report. |  |  | (1-2 days) |  | 0
| Write an executive summary. |  |  | (1-2 days)
| * Document findings, observations, and recommendations. |  |  | (3-4 days) |  | 0
| * Include relevant data, charts, and visuals. |  |  | (2-3 days) |  | 0
| * Review and edit the report for clarity and accuracy. |  |  | (1 week) |  | 0
Reporting and Feedback (Upon Completion):
| Share the draft report with site stakeholders for feedback. |  |  | (1 week)
| Address any feedback and finalize the report. |  |  | (1-2 days)
| Distribute the final report to relevant parties. |  |  | (1 day)
| * Schedule a debrief meeting with the site to discuss findings and recommendations. |  |  | (1-2 days) |  | 0
Follow-Up and Implementation (Ongoing):
| Monitor the site’s progress in implementing recommendations. |  |  | (ongoing)
Schedule follow-up visits if necessary (as needed).

## Monitoring costs
Q3 Forecast
Function | Service | Region | 2024 Q3 | 2024 Q4 | 2025 Q1 | 2025 Q2 | 2025 Q3 | 2025 Q4 | Future |  | Remaining
Global Clinical Data Management | Data Management | Global | 22760.17 | 22760.17 | 26285.88 | 23443.68 | 23443.68 | 23443.68 | 521463.4 | 663600.66 | 106646.68
Global Clinical Data Management | Database and Report Development | Global | 3883.13 | 3883.13 | 3999.74 | 3999.74 | 3999.74 | 3999.74 | 85114.95 | 108880.17 | 10650.85
Global Clinical Data Management | Statistical Programming | Global | 903.38 | 903.38 | 84303.3 | 6885.7 | 930.5 | 930.5 | 533255.65 | 628112.41 | 6829.2
Global Clinical Studies | Central Start-up | EMEA/APAC | 5531.75 | 5494.8 | 1829.63 | 1829.63 | 1829.63 | 1829.63 | 40310.09 | 58655.16 | 5206
Global Clinical Studies | Consents | Americas | 8075.05 | 7518.15 | 516.24 | 516.24 | 516.24 | 516.24 | 11022.92 | 28681.08 | 1416.8
Global Clinical Studies | Contracts | EMEA/APAC | 390.08 | 390.08 | 401.81 | 401.81 | 401.81 | 401.81 | 8583.25 | 10970.65 | 1100.25
Global Clinical Studies | Contracts | Americas | 473.37 | 473.37 | 487.56 | 487.56 | 487.56 | 487.56 | 10105.95 | 13002.93 | 1100.25
Global Clinical Studies | Payments | EMEA/APAC | 2957.58 | 2957.58 | 3056.7 | 3056.7 | 3056.7 | 3056.7 | 66225.31 | 61957.31 | 8251.25
Global Clinical Studies | Payments | Americas | 2186.4 | 2186.4 | 2252.05 | 2252.05 | 2252.05 | 2252.05 | 48576.31 | 61957.31 | 6217.2
Monitoring | Monitoring Americas | Americas | 21851.95 | 21851.95 | 22475.25 | 22475.25 | 22434.87 | 22434.87 | 484937.84 | 618461.98 | 80119.11
Monitoring | Monitoring EMEA/APAC | EMEA/APAC | 36409.11 | 36409.11 | 43412.13 | 37501.6 | 43412.13 | 37501.6 | 919040.01 | 1153685.69 | 105519.16
Operations Support | OSA | Americas | 618.65 | 618.65 | 637.2 | 637.2 | 637.2 | 637.2 | 12934.87 | 16720.97 | 38721.25
Safety | Safety | EMEA/APAC | 11635.94 | 11915.2 | 12559.03 | 12847.25 | 13154.05 | 13441.68 | 300153.05 | 375706.2 | 1016.35
Safety | Safety | Americas | 29264.44 | 29792.79 | 31130.4 | 31592.96 | 32045.45 | 32510.17 | 805522.73 | 991858.94 | 494183.45
Totals |  |  | 146941 | 147154.76 | 233346.92 | 147927.37 | 148601.61 | 143443.43 | 3847246.33 | 4814661.42 | 494183.45
SCENARIO
Function | Service | Region | 2024 | 2024 | 2025 | 2025 | 2025 | 2025 | Future |  | Remaining
Global Clinical Data Management | Data Management | Global | 22760.17 | 22760.17 | 26285.88 | 23443.68 | 23443.68 | 23443.68 | 521463.4 | 663600.66 | 106646.69
Global Clinical Data Management | Database and Report Development | Global | 3883.13 | 3883.13 | 3999.74 | 3999.74 | 3999.74 | 3999.74 | 85114.95 | 108880.17 | 10650.85
Global Clinical Data Management | Statistical Programming | Global | 903.38 | 903.38 | 84303.3 | 6885.7 | 930.5 | 930.5 | 533255.65 | 628112.41 | 6829.2
Global Clinical Studies | Central Start-up | EMEA/APAC | 5531.75 | 5494.8 | 1829.63 | 1829.63 | 1829.63 | 1829.63 | 40310.09 | 58655.16 | 5206
Global Clinical Studies | Consents | Americas | 8075.05 | 7518.15 | 516.24 | 516.24 | 516.24 | 516.24 | 11022.92 | 28681.08 | 1416.8
Global Clinical Studies | Contracts | EMEA/APAC | 390.08 | 390.08 | 401.81 | 401.81 | 401.81 | 401.81 | 8583.25 | 10970.65 | 1100.25
Global Clinical Studies | Contracts | Americas | 473.37 | 473.37 | 487.56 | 487.56 | 487.56 | 487.56 | 10105.95 | 13002.93 | 1100.25
Global Clinical Studies | Payments | EMEA/APAC | 2957.58 | 2957.58 | 3056.7 | 3056.7 | 3056.7 | 3056.7 | 66225.31 | 84367.27 | 8251.25
Global Clinical Studies | Payments | Americas | 2186.4 | 2186.4 | 2252.05 | 2252.05 | 2252.05 | 2252.05 | 48576.31 | 61957.31 | 6217.2
Monitoring | Monitoring Americas | Americas | 21851.95 | 21851.95 | 22475.25 | 22475.25 | 22434.87 | 22434.87 | 484937.84 | 618461.98 | 80119.11
Monitoring | Monitoring EMEA/APAC | EMEA/APAC | 36409.11 | 36409.11 | 43412.13 | 37501.6 | 43412.13 | 37501.6 | 919040.01 | 1153685.69 | 105519.16
Operations Support | OSA | Americas | 618.65 | 618.65 | 637.2 | 637.2 | 637.2 | 637.2 | 12934.87 | 16720.97 | 34930.07
Safety | Safety | EMEA/APAC | 11635.94 | 11766.26 | 12195.3 | 12272 | 12329.53 | 12387.65 | 271673.27 | 344259.95 | 1016.35
Safety | Safety | Americas | 29264.44 | 29587.32 | 30565.05 | 30716.22 | 30837.15 | 30927.85 | 665442.21 | 847340.24 | 472662.28
Totals |  |  | 146941 | 146800.35 | 232417.84 | 146475.38 | 146568.79 | 140807.08 | 3678686.03 | 4638696.47 | 472662.28